## Project Planner
NutriMate Project
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 Project Background and Overview | 1 | 1 | 0 | 0 | 0%
1.2 Assign Project manager | 2 | 1 |  |  | 0%
1.3 Develop Project manager | 3 | 2 |  |  | 0%
1.4 Meet stakeholders | 5 | 3 |  |  | 0%
2.1 Collect Requirement | 8 | 2 |  |  | 0%
2.2 Create Use Case Diagram | 10 | 1 |  |  | 0%
2.3 Establish Scope Plan | 11 | 3 |  |  | 0%
2.4 Create WBS | 14 | 1 |  |  | 0%
2.5 Create Gantt Chart | 14 | 2 |  |  | 0%
2.6 Software Design & System Components | 16 | 3 |  |  | 0%
2.7 Design User Interface | 19 | 3 |  |  | 0%
3.1 Develop Front-End Interface | 22 | 3 |  |  | 0%
3.2 Develop Front-End Interface | 25 | 3 |  |  | 0%
3.3 Integrate Features | 28 | 2 |  |  | 0%
3.4 Quality Assurance & Testing | 30 | 3 |  |  | 0%
3.5 Deployment | 33 | 3 |  |  | 0%
4.1 Monitor Project Work | 35 | 2 |  |  | 0%
4.2 Control Scope | 37 | 1 |  |  | 0%
4.3 Control Schedule | 38 | 2 |  |  | 0%
4.4 Perform Quality Control | 39 | 1 |  |  | 0%
4.5 Report Performance | 40 | 2 |  |  | 0%
5.1 Final Performance Review | 41 | 1 |  |  | 0%
5.2 Prepare Final Report | 42 | 2